## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | REGION VI - WESTERN VISAYAS |  | CALENDAR YEAR: | 2024
PROVINCE: | NEGROS OCCIDENTAL |  | QUARTER: | 2
CITY/MUNICIPALITY: | CITY OF SAN CARLOS
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development (pls list down specific projects) | [5 empty] | 4178517.63
Dev't and Construction of Brgy. Facilities and other Gov't Facilities
1. Const. of riprap and slope protection of concrete road along Ledesma
Heights riverbank |  | 2690000 | 2024-02-19 |  |  | 1155856.32 |  | on-going
2. Water system for san carlos City Tree Park |  | 1950000 | 2024-02-19 |  |  | 671228.75 |  | on-going
3. Rehabilitation of Consuelo Community Center |  | 3700000 | 2024-02-19 |  |  | 640837.5 |  | on-going
4. Install. Of devices insid and outside the perimeter of various government
facilities for pest control |  | 2000000 | 2024-03-18 |  |  | 0 |  | on-going
5. Rehabilitation of Brgy. 6 covered court roofing |  | 1800000 | 2024-04-18 |  |  | 23019.94 |  | on-going
Water Development Program
1. Level II water system at Purok Ananhaw, So. Lupao, Brgy. Quezon |  | 1550000 | 2024-02-02 |  |  | 499067.6 |  | on-going
2. Rehabilitation and improvement of weir |  | 1160000 | 2024-02-06 |  |  | 515180.62 |  | on-going
3. Re-alignment of stub-out |  | 255000 | 2024-02-06 |  |  | 193446.87 |  | on-going
4. Construction of Sta. Ana well pumping station |  | 1000000 | 2024-02-06 |  |  | 273617.93 |  | on-going
5. Embedment and realignment of stub-outs |  | 550000 | 2024-03-18 |  |  | 206262.1 |  | on-going
6. Improvement of mainline interconnection at Medina Translink Highway |  | 345000 | 2024-03-25 |  |  | 0 |  | on-going
7. Backfilling of road network at water treatment plant site |  | 300000 | 2024-04-11 |  |  | 0 |  | on-going
8. Water tank in-place strenght test |  | 50600 |  |  |  | 0 |  | on-going
Acq./const./development of facilities (Sports)
1. Rehabilitation of boxing gym at Brgy. I |  | 567000 | 2024-03-18 |  |  | 0 |  | on-going
2. Rehab. Of 2 football field |  | 582800 | 2024-06-26 |  |  | 0 |  | on-going
Acq./const./development of facilities (Sports)
1.Const. of San carlos City superhealth center (medium) Phase 2, Brgy. Prosperidad |  | 6200000 | 2024-04-18 |  |  | 0 |  | on-going
Economic Development (pls list down specific projects) | [5 empty] | 431030
Roads Development Program
1. Road opening at So. Brillantes to So. Ansulag, Brgy. Rizal |  | 725000 | 2024-02-19 | (CY 2023 1,125,000.00) |  | 17490 |  | on-going
2. Road concreting from Pamahawan to Mangga road |  | 5785000 | 2024-02-19 |  |  | 0 |  | on-going
3. Road concreting of 6th street road at So. Lawis, Brgy. Buluangan |  | 745000 | 2024-02-19 |  |  | 28800 |  | on-going
4. Restoratin of concrete paved road along So. Matunog, Brgy. Bagonbon |  | 1400000 | 2024-05-07 |  |  | 0 |  | on-going
5. Concreting of road along Katiclan tree park to Ansulag |  | 5000000 | 2024-05-23 |  |  | 0 |  | on-going
6. Concreting of identified road shoulders at San Carlos City |  | 4200000 | 2024-05-07 |  |  | 0 |  | on-going
7. Concreting along Iliranan to So. Apog-apog (phase 4), Brgy. Codcod |  | 10000000 | 2024-06-26 |  |  | 0 |  | on-going
Acq./const./development of land and facilities - Tourism
1. Const. and improvement of SCC pavillion and display booths at Panaad
Park Stadium |  | 450000 | 2024-03-13 |  |  | 384740 |  | on-going
2. Const. (civil works) of 2 units dancing fountain at SCC City Hall |  | 2960000 | 2024-04-18 |  |  | 0 |  | on-going
3. Rehab. Of waterfalls and fishpond at People's Park |  | 600000 | 2024-05-06 |  |  | 0 |  | on-going
4. Purchase and install. Of motor pump and filter elements for swimming pool |  | 437000 | 2024-05-06 |  |  | 0 |  | on-going
5. Install. Of garden water sprinkler system at People's Park |  | 205000 | 2024-05-15 |  |  | 0 |  | on-going
6. Improvement of People's Park facilities and other structures |  | 1800000 | 2024-06-26 |  |  | 0 |  | on-going
Environment Development (pls list down specific projects) | [5 empty] | 19340785.48
1. eco-center project operation |  | 2500000 | 2024-02-06 |  |  | 1518632.6 |  | on-going
2. Improvement and development of city lanes and city streets |  | 3746150 | 2024-02-06 |  |  | 3630247.25 |  | on-going
3. Sanitation and environmental protection program |  | 4249810 | 2024-02-06 |  |  | 3451605.63 |  | on-going
4. Const. of material recovery facility extension and supply and installation of
waste processing (Pyrolysis) equipment |  | 24500000 | 2024-03-05 |  |  | 0 |  | on-going
Purchase of Engineering Heavy Equipments, Accessories and Other Engineering Equipment
1. Purchase of 1 crawler type hydraulic excavator |  | 10730000 | 2024-02-02 |  |  | 10725000 |  | completed
2. Purchase of 1 unit cargo truck |  | 4200000 | 2024-03-18 |  |  | 0 |  | on-going
3. Purchase of universal testing machine |  | 1650000 | 2024-05-07 |  |  | 0 |  | completed
4. Purchase of digital rebound test hammer |  | 160000 | 2024-05-07 |  |  | 0 |  | on-going
Construction/Rehabilitation of Drainage System
1. Fabrication and installation of reinforced concrete pipe culvert for various
barangays |  | 300000 | 2024-03-18 |  |  | 15300 |  | on-going
2. Install. Of reinforced concrete pipe culvert along Adjacket to
So. Natuyay road, Brgy. Quezon |  | 630000 | 2024-09-11 |  |  | 0 |  | on-going
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
(SGD) SANDRA LUZ B. BRIONES |  |  |  |  | (SGD) RENATO Y. GUSTILO
Local Budget Officer |  |  |  |  | Local Chief Executive

## Sheet1
1. Const. of riprap and slope protection of concrete road along Ledesma
Heights riverbank | 2690000 | 45341 | 0 | on-going
2. Water system for san carlos City Tree Park | 1950000 | 45341 | 0 | on-going
3. Rehabilitaqtion of Consuelo Community Center | 3700000 | 45341 | 21105 | on-going
4. Install. Of devices insid and outside the perimeter of various government
facilities for pest control | 2000000 | 45369 |  | on-going
1. Const. of riprap and slope protection of concrete road along Ledesma
Heights riverbank | 2690000 | 2024-02-19 | 0 | on-going
2. Water system for san carlos City Tree Park | 1950000 | 2024-02-19 | 0 | on-going
3. Rehabilitaqtion of Consuelo Community Center | 3700000 | 2024-02-19 | 21105 | on-going
4. Install. Of devices insid and outside the perimeter of various government
facilities for pest control | 2000000 | 2024-03-18 |  | on-going

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2