## 4TH quarter2024
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
REGION: | REGION VI - WESTERN VISAYAS |  | CALENDAR YEAR: | 2024
PROVINCE: | NEGROS OCCIDENTAL |  | QUARTER: | 3
CITY/MUNICIPALITY: | CITY OF SAN CARLOS
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
PAMANA FUND
1. KAPATIRAN (Office of the Presidential Adviser for Peace Process) | San Carlos City
-Const. of Peace and Development Center | Barangay Bagonbon | 5000000 | November 2021 |  |  | 4976041.41
-Const .of Temporary Shelter at PDC Site So. Nangka, Brgy. Bagonbon | Barangay Bagonbon | 300000 | August 2023 |  |  | 209063.8
-Const. of Production or Processing Area at So. Nangka, Brgy. Bagonbon | Barangay Bagonbon | 800000 | June 2022 |  |  | 575794.85
-Const. of 60 Heads Fattening Pigpen at So. Nangka, Brgy. Bagonbon | Barangay Bagonbon | 340000 | October 2023 |  |  | 0
-Const. of 15 Heads Cow Fattening Shed at So. Medina, Brgy. Rizal | Barangay Bagonbon | 200000 | November 2023 |  |  | 0
-Livelihood Program | Barangay Bagonbon | 4000000 | July 2021 |  |  | 2773617.96 |  |  | 10710020-001-000267
[9 empty] | 20201050-011-000017 | 8994561.5
2. BOTTOM-UP BUDGETING | [9 empty] | #REF!
-Establishment of Mangrove Eco-Park | San Carlos City | 800000 | September 2015 |  |  | 771378
-Zero Waste Kabuhayan sa Abaca | San Carlos City | 900000 | June 2016 |  |  | 681411.95
-Establishment of Deep Sea Fish Coral ( DUMPIL ) | San Carlos City | 1000000 | Nov. 2016 |  |  | 939485
-SCAPODA Spareparts Kabuhayan, Dole - RVI | San Carlos City | 500000 | April 2018 |  |  | 348675.55
-SABON Kabuhayan for Women | San Carlos City | 500000 | April 2018 |  |  | 499575
-PUMPBOAT Kabuhayan, DOLE - RVI | San Carlos City | 500000 | April 2018 |  |  | 256898.9
3. RARE INC.
-SCC Fish Forever Pride Campaign | San Carlos City | 550000 | March 2015 |  |  | 331623.5 |  |  |  | 218376.5
4. LOCAL GOVERNMENT SUPPORT FUND
-Bureau of Fire Protection | San Carlos City | 530367 | September 2021 |  |  | 525038 |  |  | 10710020-001-000023 | 5329
Const. of Public Parks and Plazas of the City of San Carlos | San Carlos City | 20000000 | October 2023 |  |  | 18000000 |  |  | 20201050-002-000005 | 2000000
5) DEPARTMENT OF HEALTH-CHD, RVI
Improvement of TB DOTS Facility at the City Hospital | San Carlos City | 150000 | May 2015 |  |  | 149450 |  |  | 10710030-001-000067 | 550
Construction of San Carlos City Super Health Center | San Carlos City | 6000000 | May 2023 |  |  | 5972711.28
6) DEPARTMENT OF SOCIAL WELFARE AND DEVELOPMENT OFFICE
14th Cycle of Supplemental Feeding Program of Day Care Pre-schoolers | San Carlos City | 5479200 | October 2024 |  |  | 2739600 |  |  | 20201050-011-000019 | 344214.85 | 492818.89
Social Pension of Indigent Senior Citizens | San Carlos City | 5721000 | October 2024 |  |  | 5721000 |  |  |  | 5134985.15
7) BUREAU OF FISHERIES AND AQUATICE RESOURCES (BFAR)
Purchase of Various Equipments for Bantay Dagat Program | San Carlos City | 500000 | September 2023
8) DEPARTMENT OF INTERIOR & LOCAL GOV'T. (DILG)
Purchase of Virtual Production Equipment (PCF) | San Carlos City | 2300000 | January 2024 |  |  | 2300000
9. DEPARTMENT OF AGRICULTURE
Catalytic Fund for the Establishment of FITS Center | San Carlos City | 100000 | November 2024
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
(SGD) SANDRA LUZ B. BRIONES |  |  | (SGD) JOSE VENFORT L. LEGARIA, CPA |  |  | (SGD) RENATO Y. GUSTILO
Local Budget Officer |  |  | Local Accountant |  |  | Local Chief Executive

## Form 6b - TFU (hidden)
LOCAL GOVERNMENT SUPPORT FUND (Report on Fund Utilization and Status of Program/Project Implementation)
REGION: |  |  | CALENDAR YEAR:
PROVINCE: |  |  | QUARTER:
CITY/MUNICIPALITY: |  |  | OFFICE:
Amount
Fund Source | Date of Notice of Authority to Debit Account Issued | Type of Program/Project | Name Title of Program/Project | Specific Location | Mechanism/Mode of Implementation | Estimated Number of Beneficiaries | Received | Obligation | Disbursement | Estimated Completion (Month and Year) | Remarks on Program/Project Status
Certified Correct by: |  |  |  |  | Attested by:
The Local Finance Committee:
Local Chief Executive
City Budget Officer
City Treasurer
City Planning and Development Coordinator
Instructions:
1 | The report shall prepared by the LFC, in coordination with the other local officials concerned (local accountant on the allotment, obligation and disbursements;
local engineers in the status of infrastructure projects, as may be applicable.
2 | The fund source shall be based on the NADAI issued to the cities.
3 | The type of program/project shall be identified, consistent with the projects that may be implemented under the Circular.
4 | Amount received refers to the amount received by the city as its location. It is the amount the NADAI. Obligation refers to the total amount obligated by the
city as of reporting period. Disbursement refers to the total amount paid as of reporting period.
5 | The status of programs/projects refers to the percentage of physical completion or delivery of service as of reporting period.

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2