## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | REGION VI - WESTERN VISAYAS |  | CALENDAR YEAR: | 2024
PROVINCE: | NEGROS OCCIDENTAL |  | QUARTER: | 4
CITY/MUNICIPALITY: | CITY OF SAN CARLOS
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development (pls list down specific projects) | [5 empty] | 20615721.433
Dev. and Const. of Barangay Facilities and other Government facilities
1. Const. of riprap and slope protection of concrete road along Ledesma
Heights riverbank |  | 2690000 | 2024-02-19 |  |  | 2403763.14 |  | on-going
2. Water system for san carlos City Tree Park |  | 1950000 | 2024-02-19 |  |  | 1221672.57 |  | on-going
3. Rehabilitation of Consuelo Community Center |  | 3700000 | 2024-02-19 |  |  | 2928857.5 |  | on-going
4. Install. Of devices insid and outside the perimeter of various government
facilities for pest control |  | 2000000 | 2024-03-18 |  |  | 1900700 |  | on-going
5. Rehabilitation of Brgy. 6 covered court roofing |  | 1800000 | 2024-04-18 |  |  | 1438830.59 |  | on-going
6. Slope protection along Baticulan creek from Palampas to Brgy. 6 |  | 1000000 | 2024-07-29 | Augmentation to CY 2023
7. Rehabilitation of PESO livelihhod and training center perimeter fence and training room |  | 420000 | 2024-07-22 |  |  | 159850 |  | on-going
8. Rehabilitation of irrigation lined canal at So. Walos |  | 280000 | 2024-10-16 |  |  | 11398 |  | on-going
9. Construction of senior citizen building |  | 5200000 | 2024-10-16 |  |  | 0 |  | on-going
10. Construction of MPDP at Purok Santan, Brgy. Bagonbon |  | 790000 | 2024-12-26 |  |  | 0 |  | on-going
Water Development Program
1. Level II water system at Purok Ananhaw, So. Lupao, Brgy. Quezon |  | 1550000 | 2024-02-02 |  |  | 1198882.68 |  | on-going
2. Rehabilitation and improvement of weir |  | 1160000 | 2024-02-06 |  |  | 973996.26 |  | on-going
3. Re-alignment of stub-out |  | 255000 | 2024-02-06 |  |  | 201246.87 |  | on-going
4. Construction of Sta. Ana well pumping station |  | 1000000 | 2024-02-06 |  |  | 681458.093 |  | on-going
5. Embedment and realignment of stub-outs |  | 550000 | 2024-03-18 |  |  | 386014.4 |  | on-going
6. Improvement of mainline interconnection at Medina Translink Highway |  | 345000 | 2024-03-25 |  |  | 1073 |  | on-going
7. Backfilling of road network at water treatment plant site |  | 300000 | 2024-04-11 |  |  | 0 |  | on-going
8. Water tank in-place strenght test |  | 50600 |  |  |  | 0 |  | on-going
9. Improvement of South villa 3 pumping station |  | 1950000 | 2024-07-12 |  |  | 1790000 |  | on-going
10. Rerouting of 3 pahase line and transfer of 3 pcs. 37.5 KVA transformer at
South villa III water supply station |  | 625000 | 2024-07-23 |  |  | 360241 |  | on-going
Acq./Const./Development of facilities (Sports)
1. Rehabilitation of boxing gym at Brgy. I |  | 567000 | 2024-03-18 |  |  | 378647.1 |  | on-going
2. Rehab. Of 2 football field |  | 582800 | 2024-06-26 |  |  | 84400 |  | on-going
3. Fabrication of futsal goals at City sports Park |  | 72000 | 2024-10-16 |  |  | 42226 |  | on-going
4. Construction of billard hall at City Spotrs Park |  | 1500000 | 2024-12-26 |  |  | 0 |  | on-going
CONSTRUCTION AND DEVELOPMENT OF CITY HOSPITAL AND OTHER HEALTH FACILITIES
1.Const. of San carlos City superhealth center (medium) Phase 2, Brgy. Prosperidad |  | 6200000 | 2024-04-18 |  |  | 4029923.23 |  | on-going
2. Rehabilitation of floor tiles for new City Hospital (phase 4) |  | 520000 | 2024-08-02 |  |  | 293420 |  | on-going
3. Improvement of primary care facility |  | 220000 | 2024-09-11 |  |  | 129121 |  | on-going
Economic Development (pls list down specific projects) | [5 empty] | 7090247.62
ROAD DEVELOPMENT PROGRAM
1. Road opening at So. Brillantes to So. Ansulag, Brgy. Rizal |  | 725000 | 2024-02-19 | (CY 2023 1,125,000.00) |  | 201487.5 |  | on-going
2. Road concreting from Pamahawan to Mangga road |  | 5785000 | 2024-02-19 |  |  | 17707.5 |  | on-going
3. Road concreting of 6th street road at So. Lawis, Brgy. Buluangan |  | 745000 | 2024-02-19 |  |  | 376123.42 |  | on-going
4. Restoratin of concrete paved road along So. Matunog, Brgy. Bagonbon |  | 1400000 | 2024-05-07 |  |  | 205163 |  | on-going
5. Concreting of road along Katiclan tree park to Ansulag |  | 5000000 | 2024-05-23 |  |  | 0 |  | on-going
6. Concreting of identified road shoulders at San Carlos City |  | 4200000 | 2024-05-07 |  |  | 0 |  | on-going
7. Concreting along Iliranan to So. Apog-apog (phase 4), Brgy. Codcod |  | 10000000 | 2024-06-26 |  |  | 0 |  | on-going
8. Concreting of road along So. Sto. Rosario to Rizal proper |  | 10000000 | 2024-10-16 |  |  | 0 |  | on-going
9. Application of sub-base materials for various barangays |  | 13000000 | 2024-10-16 |  |  | 0 |  | on-going
10. Road concreting with draingae inside agriculture compound (Phase 1) |  | 5200000 | 2024-11-07 |  |  | 0 |  | on-going
11. Concreting of road along Balabag E/S |  | 10000000 | 2024-12-26 |  |  | 0 |  | on-going
12. Restoration of concrete paved (one lane) at So. Mag-amihan, Brgy. Punao |  | 672000 | 2024-12-26 |  |  | 0 |  | on-going
Acq./const./development of land and facilities - Tourism
1. Const. and improvement of SCC pavillion and display booths at Panaad
Park Stadium |  | 450000 | 2024-03-13 |  |  | 384740 |  | on-going
2. Const. (civil works) of 2 units dancing fountain at SCC City Hall |  | 2960000 | 2024-04-18 |  |  | 2636554.2 |  | on-going
3. Rehab. Of waterfalls and fishpond at People's Park |  | 600000 | 2024-05-06 |  |  | 468121.5 |  | on-going
4. Purchase and install. Of motor pump and filter elements for swimming pool |  | 437000 | 2024-05-06 |  |  | 434000 |  | on-going
5. Install. Of garden water sprinkler system at People's Park |  | 205000 | 2024-05-15 |  |  | 195448 |  | on-going
6. Improvement of People's Park facilities and other structures |  | 1800000 | 2024-06-26 |  |  | 1248655.4 |  | on-going
7. Construction of additional floating dock at Park Marina |  | 4000000 | 2024-06-26 |  |  | 0 |  | on-going
8. Architectural works for 2 units dancing fountain at SCC City Hall |  | 1450000 |  |  |  | 922247.1 |  | on-going
Environmental Management (pls list down specific projects) | [5 empty] | 64609745.5
1. Eco-Center project operation |  | 4983640 | 2024-02-06 |  |  | 4022720.03 |  | completed
2. Improvement and development of city lanes and city streets |  | 10114410 | 2024-02-06 |  |  | 9692025.13 |  | completed
3. Sanitation and environmental protection program |  | 9818710 | 2024-02-06 |  |  | 9012749.84 |  | completed
4. Const. of material recovery facility extension and supply and installation of |  |  |  | Sp Ordinance #24-309 (CANCELLED)
waste processing (Pyrolysis) equipment |  | 24500000 | 2024-03-05
4. Supply and installation of waste processing plant (Pyrolysis0 equipment |  | 21000000 | 2024-08-30 | CY 2023 24,000,000.00 |  | 0 |  | on-going
5. Construction of material recovery facility extension |  | 3500000 | 2024-08-30 |  |  | 0 |  | on-going
6. Procurement of 22 units garbage motorcycle |  | 6600000 | 2024-08-30 |  |  | 6600000 |  | completed
7. Rehabilitaion of sanitary landfill |  | 3000000 | 2024-10-11 |  |  | 0 |  | on-going
Purchase of Engineering Heavy Equipments, Accessories and Other Enginnering Equipment
1. Purchase of 1 crawler type hydraulic excavator |  | 10730000 | 2024-02-02 |  |  | 10725000 |  | completed
2. Purchase of 1 unit cargo truck |  | 4200000 | 2024-03-18 |  |  | 4178000 |  | completed
3. Purchase of universal testing machine |  | 1650000 | 2024-05-07 |  |  | 1648080 |  | completed
4. Purchase of digital rebound test hammer |  | 160000 | 2024-05-07 |  |  | 160000 |  | completed
Construction/Rehabilitation of Drainage System
1. Fabrication and installation of reinforced concrete pipe culvert for various
barangays |  | 300000 | 2024-03-18 |  |  | 225632.4 |  | on-going
2. Install. Of reinforced concrete pipe culvert along Adjacket to
So. Natuyay road, Brgy. Quezon |  | 630000 | 2024-09-11 |  |  | 494690.5 |  | on-going
3. Construction of masonry lined canal (Phase2) at So. Apog-apog |  | 2950000 | 2024-08-02 |  |  | 794498.7 |  | on-going
4. Construction of masonry lined canal along So. Balabag, Brgy. Quezon |  | 3000000 | 2024-08-29 |  |  | 689913.5 |  | on-going
5. Fabrication of reinforced concrete pipe culvert for drainage improvement from
Locsin street going Parola outfall |  | 4250000 | 2024-09-10 |  |  | 376265.5 |  | on-going
6. Restoration of concrete sidewalks, curb and gutters and manhole covers,
and declogging of drainage going to outfalls within city proper |  | 2000000 | 2024-09-10 |  |  | 757930.49 |  | on-going
7. Construction of storm drainage at City Hospital |  | 1140000 | 2024-11-07 |  |  | 0 |  | on-going
Electrification of City Roads/Installation of lighting system
1. Slaughterhouse street lighting |  | 160000 | 2024-06-25 |  |  | 114859 |  | on-going
2. Electrical supply fro 2 units dancing fountain at City Hall |  | 1000000 | 2024-06-26 |  |  | 846637.41 |  | on-going
3. Purchase of 50KVA transformer for trade fair area |  | 191000 | 2024-08-07 |  |  | 168000 |  | on-going
4. Relocation of street lights posts from gutter to sidewalk along Locsin st. (19 post) |  | 257000 | 2024-09-02 |  |  | 135778 |  | on-going
5. Medium to low voltage supply for San Carlos tree park |  | 4000000 | 2024-09-02 |  |  | 0 |  | on-going
Development of Public Market and Slaughterhouse
1. Rehabilitation of wet market, stalls and gratings at Brgy. IV |  | 2850000 | 2024-07-10 |  |  | 0 |  | on-going
2. rehabilitation of 5 units food stalls at farmer's Market |  | 2000000 | 2024-09-24 |  |  | 0 |  | on-going
Construction of Bulkhead and embankment for Various Barangays
1. Construction and development of land circunferential road at various barangays
(Barangay 5 and 6 ) filling for embankment |  | 15000000 | 2024-05-29 |  |  | 13966965 |  | on-going
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| (SGD) SANDRA LUZ B. BRIONES |  |  |  | (SGD) RENATO Y. GUSTILO
| Local Budget Officer |  |  |  | Local Chief Executive

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2