## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | NIR-NEGROS ISLAND REGION |  | CALENDAR YEAR: | 2025
PROVINCE: | NEGROS OCCIDENTAL |  | QUARTER: | 1
CITY/MUNICIPALITY: | CITY OF SAN CARLOS
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development (pls list down specific projects) | [5 empty] | 76175.7
Dev. and Const. of Barangay Facilities and other Government facilities | SAN CARLOS CITY, NEG. OCC.
1. Concreting of pavement at motorpool area from entrance to GSD | SAN CARLOS CITY, NEG. OCC.
warehouse (Phase1) | SAN CARLOS CITY, NEG. OCC. | 3150000 | 2025-02-21 |  |  | 0 |  | on-going
2. Concreting of pavement and fencing at DENR training center | SAN CARLOS CITY, NEG. OCC. | 2969384 | 2025-03-21 |  |  | 0 |  | on-going
Water Development Program
1. Stub-out embedment and realignment | SAN CARLOS CITY, NEG. OCC. | 500000 | 2025-02-13 |  |  | 16394.4 |  | on-going
2. Installation of additional waterline at the city main water system | SAN CARLOS CITY, NEG. OCC. | 1500000 | 2025-02-13 |  |  | 0 |  | on-going
3. Installation of air release valves at strategic points | SAN CARLOS CITY, NEG. OCC. | 400000 | 2025-02-13 |  |  | 0 |  | on-going
4. Improvement of cluttered level III in-house service connections | SAN CARLOS CITY, NEG. OCC. | 1000000 | 2025-02-13 |  |  | 59781.3 |  | on-going
5. Improvement of Bodiawe pumping station | SAN CARLOS CITY, NEG. OCC. | 1500000 | 2025-02-13 |  |  | 0 |  | on-going
6. Improvement of seaside pumping station | SAN CARLOS CITY, NEG. OCC. | 1000000 | 2025-02-13 |  |  | 0 |  | on-going
7. Improvement of Brgy. Quezon water supply system | SAN CARLOS CITY, NEG. OCC. | 750000 | 2025-02-13 |  |  | 0 |  | on-going
Acq./Const./Development of facilities (Sports)
1. Construction of 2 tennis courts at Park Marina | SAN CARLOS CITY, NEG. OCC. | 4000000 | 2025-03-21 |  |  | 0 |  | on-going
CONSTRUCTION AND DEVELOPMENT OF CITY HOSPITAL AND OTHER HEALTH FACILITIES
1. Development of fitness playground at San Carlos City Hospital | SAN CARLOS CITY, NEG. OCC. | 2047350 | 2025-03-21 |  |  | 0 |  | on-going
Economic Development (pls list down specific projects) | [5 empty] | 485292
ROAD DEVELOPMENT PROGRAM
1. Road opening at So. Brillantes | SAN CARLOS CITY, NEG. OCC. | 2000000 | 2025-03-21 |  |  | 0 |  | on-going
2. Concreting of road at So. Brillantes | SAN CARLOS CITY, NEG. OCC. | 10000000 | 2025-03-21 |  |  | 0 |  | on-going
3. Concreting of road at So. Gigalaman, Brgy. Guadalupe | SAN CARLOS CITY, NEG. OCC. | 10000000 | 2025-03-31 |  |  | 0 |  | on-going
Acq./const./development of land and facilities - Tourism
1. Const. and improvement of SCC pavillion and display booths at Panaad Park Stadium | SAN CARLOS CITY, NEG. OCC. | 640000 | 2025-01-31 |  |  | 485292 |  | on-going
2. Addition of lighting system of the 2 interactive musical fountain | SAN CARLOS CITY, NEG. OCC. | 4000000 | 2025-03-21 |  |  | 0 |  | on-going
Environmental Management (pls list down specific projects) | [5 empty] | 3905499.93
Various Environmental Projects
1. Purchase of 1 unit vacuum truck | SAN CARLOS CITY, NEG. OCC. | 11500000 | 2025-02-11 |  |  | 0 |  | on-going
2. eco-center project operation | SAN CARLOS CITY, NEG. OCC. | 8038300 | 2025-02-11 |  |  | 717255 |  | on-going
3. Improvement and development of city lanes and city streets | SAN CARLOS CITY, NEG. OCC. | 9247907.93 | 2025-02-11 |  |  | 1699907.93 |  | on-going
4. Sanitation and environmental protection program | SAN CARLOS CITY, NEG. OCC. | 16234000 | 2025-02-11 |  |  | 1488337 |  | on-going
Purchase of Engineering Heavy Equipments, Accessories and Other Engineering Equipment
1. Purchase of 1 unit single drum vibrator road roller and 1 unit forklift | SAN CARLOS CITY, NEG. OCC. | 8000000 | 2025-01-30 |  |  | 0 |  | on-going
2, Purchase of 2 units brand new water tanker | SAN CARLOS CITY, NEG. OCC. | 9700000 | 2025-03-21 |  |  | 0 |  | on-going
Electrification of City Roads/Inatallation of lighting system
1. Relocation of street lights posts from gutter to sidewalk along Gustilo street (23 posts) | SAN CARLOS CITY, NEG. OCC. | 414000 | 2025-02-26 |  |  | 0 |  | on-going
Construction of Bulkhead and Embankment of various barangays
1. Const, and development of land circumferential road at various barangays | SAN CARLOS CITY, NEG. OCC.
(Brgy. 5 and 6 ) filling for embankment |  | 5000000 | 2025-03-21 |  |  | 0 |  | on-going
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| (SGD) SANDRA LUZ B. BRIONES |  |  |  | (SGD) RENATO Y. GUSTILO
| Local Budget Officer |  |  |  | Local Chief Executive

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2